## Sheet1
Defect ID | Defect Summary | Detected By | Detection Date | Subject | Status | Severity | Priority | Assigned to | Actual Fix Time | Closing Date | Dev Comments | Detected in Phase | Root Cause | Detected in Cycle | Application under Test | Description
1 | ABCD 1231: Status coming on Web UI is different | MarthaN | 2020-08-01 | ABCD 1231 : Web UI Validation | Closed | 3 - Non-Critical | 2 - Medium | JonasK | 3 | 2020-08-04 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | Technical constraints | SIT1 | WEB1 | Status shown is declined instead of approved
2 | ABCD 1231: Field is missing on Web UI | HannahK | 2017-10-12 | ABCD 1231 : Web UI Validation | Awaiting Retest | 2 - Critical | 1 - High | NoahMC | 4 | 2017-10-16 | Decision machine is down | PAT | Code | SIT2 | WEB2 | Field A is missing on Web UI
3 | ABCD 1231: Field is added on Web UI | UlrichN | 2017-04-19 | ABCD 1231 : Web UI Validation | Deferred | 1 - Showstopper | 1 - High | AdamMC | 6 | 2017-04-25 | CB Pull is down | PROD | Data | UAT1 | WEB3 | Field A is added on UI
4 | ABCD 1231: Field value is different on Web UI | AgnesN | 2016-11-01 | ABCD 1231 : Web UI Validation | Fixed | 4 - Live with | 3 - Low | HelgeD | 13 | 2016-11-14 | MQ is down | UAT | Design | UAT2 | WEB4 | Field A is showing different value
5 | ABCD 1231: Field value is different on Web UI | ClaudiaT | 2016-03-07 | ABCD 1231 : Web UI Validation | Monitor | 2 - Critical | 1 - High | AleksanderT | 7 | 2016-03-14 | We are looking for the root cause | DIT | Development Documentation | Sprint1 | Windows1 | Field A is showing different value
6 | ABCD 1231: Field value is different on Web UI | CharlotteD | 2017-01-28 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | MikkelN | 14 | 2017-02-11 | We are looking for the root cause | SPRINT | Duplicate | Sprint2 | Windows2 | Field A is showing different value
7 | ABCD 1231: Status coming on Web UI is different | KatharinaN | 2019-04-08 | ABCD 1231 : Web UI Validation | Open | 3 - Non-Critical | 2 - Medium | ElisabethD | 10 | 2019-04-18 | CB Pull is down | SIT | Existing Production defect | Sprint3 | Windows3 | Status shown is Passed instead of failed
8 | ABCD 1231: Status coming on Web UI is different | BerndD | 2019-02-09 | ABCD 1231 : Web UI Validation | Production | 3 - Non-Critical | 2 - Medium | EgonT | 7 | 2019-02-16 | CB Pull is down | SIT | not a variance | Sprint4 | Windows4 | Status shown is Passed instead of failed
9 | ABCD 1231: Status coming on Web UI is different | AleksanderT | 2019-12-22 | ABCD 1231 : Web UI Validation | Rejected | 3 - Non-Critical | 2 - Medium | NoahMC | 7 | 2019-12-29 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | not yet analyzed | Sprint5 | Windows5 | Status shown is declined instead of approved
10 | ABCD 5696 : Status coming is different on Windows UI | InesK | 2016-02-18 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | NoahMC | 6 | 2016-02-24 | Decision machine is down | SIT | Test case | CR1 | WEB3 | Status shown is Passed instead of failed
11 | ABCD 5696 : Field is missing on Windows UI | HelgeD | 2020-10-05 | ABCD 5696 : Windows UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 13 | 2020-10-18 | Decision machine is down | SIT | test environment | CR2 | WEB2 | Field A is missing on Windows UI
12 | ABCD 5696 : Field is added on Windows UI | PeterD | 2016-11-16 | ABCD 5696 : Windows UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 2 | 2016-11-18 | Decision machine is down | SIT | Business Requirements | CR3 | WEB2 | Field A is added on UI
13 | ABCD 5696 : Field value is different on Windows UI | ErikO | 2019-05-06 | ABCD 5696 : Windows UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 12 | 2019-05-18 | Decision machine is down | SPRINT | solution requirements | CR4 | WEB2 | Field A is showing different value
14 | ABCD 1231: Status coming on Web UI is different | ElisabethD | 2016-03-14 | ABCD 1231 : Web UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 5 | 2016-03-19 | Decision machine is down | SPRINT | Development Documentation | CR5 | WEB1 | Status shown is Passed instead of failed
15 | ABCD 1231: Status coming on Web UI is different | JonasK | 2016-07-26 | ABCD 1231 : Web UI Validation | Closed | 3 - Non-Critical | 2 - Medium | NoahMC | 2 | 2016-07-28 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SPRINT | Development Documentation | Before Code | WEB1 | Status shown is declined instead of approved
16 | ABCD 1231: Status coming on Web UI is different | JonasK | 2017-06-03 | ABCD 1231 : Web UI Validation | Closed | 3 - Non-Critical | 2 - Medium | AdamMC | 8 | 2017-06-11 | Decision machine is down | UAT | Development Documentation | PAT Apr | WEB1 | Status shown is declined instead of approved
17 | ABCD 1231: Status coming on Web UI is different | JonasK | 2019-04-27 | ABCD 1231 : Web UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 15 | 2019-05-12 | Decision machine is down | SIT | Design | PAT May | WEB1 | Status shown is Passed instead of failed
18 | ABCD 1231: Status coming on Web UI is different | JonasK | 2016-11-28 | ABCD 1231 : Web UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | HelgeD | 4 | 2016-12-02 | Decision machine is down | SIT | Code | PAT Oct | WEB1 | Status shown is Passed instead of failed
19 | ABCD 1231: Status coming on Web UI is different | HannahK | 2018-01-11 | ABCD 1231 : Web UI Validation | Fixed | 2 - Critical | 1 - High | HelgeD | 6 | 2018-01-17 | Decision machine is down | SIT | Code | SIT1 | WEB1 | Status shown is Passed instead of failed
20 | ABCD 1231: Status coming on Web UI is different | HannahK | 2019-12-13 | ABCD 1231 : Web UI Validation | Deferred | 2 - Critical | 1 - High | EgonT | 11 | 2019-12-24 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | Code | SIT2 | WEB1 | Status shown is Passed instead of failed
21 | ABCD 1231: Field is missing on Web UI | ClaudiaT | 2016-06-03 | ABCD 1231 : Web UI Validation | Production | 2 - Critical | 1 - High | EgonT | 1 | 2016-06-04 | Decision machine is down | SIT | Code | SIT2 | Windows1 | Field b is missing on Web UI
22 | ABCD 1231: Field is missing on Web UI | ClaudiaT | 2017-09-30 | ABCD 1231 : Web UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 15 | 2017-10-15 | Decision machine is down | SIT | Code | SIT2 | Windows1 | Field c is missing on Web UI
23 | ABCD 1231: Field is added on Web UI | ClaudiaT | 2020-07-27 | ABCD 1231 : Web UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 13 | 2020-08-09 | Decision machine is down | SIT | Code | SIT1 | WEB2 | Field B is added on web UI
24 | ABCD 2258 : Web Application is showing low performance on heavy load | UlrichN | 2019-10-25 | ABCD 2258 : Web PAT Validation | Closed | 2 - Critical | 1 - High | NoahMC | 7 | 2019-11-01 | Decision machine is down | SIT | Code | SIT1 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
25 | ABCD 2258 : Web Application is showing low performance on normal load | UlrichN | 2016-06-02 | ABCD 2258 : Web PAT Validation | Closed | 4 - Live with | 3 - Low | AdamMC | 12 | 2016-06-14 | Decision machine is down | SIT | Code | SIT1 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
26 | ABCD 2258 : Web Application is showing low performance on normal load | JonasK | 2018-06-07 | ABCD 2258 : Web PAT Validation | Closed | 1 - Showstopper | 1 - High | AdamMC | 6 | 2018-06-13 | We are looking for the root cause | SIT | Code | SIT1 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
27 | ABCD 2258 : Web Application is showing low performance on normal load | JonasK | 2017-06-15 | ABCD 2258 : Web PAT Validation | Closed | 4 - Live with | 3 - Low | AleksanderT | 1 | 2017-06-16 | CB Pull is down | UAT | Code | SIT1 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
28 | ABCD 2258 : Windows Application is showing low performance on normal load | JonasK | 2020-10-31 | ABCD 1147 : Windows PAT Validation | Closed | 1 - Showstopper | 1 - High | NoahMC | 3 | 2020-11-03 | CB Pull is down | UAT | Code | SIT2 | WEB1 | The performance of the system is lagging by 30 seconds on normal load.
29 | ABCD 5696 : Field is missing on Windows UI | JonasK | 2019-09-22 | ABCD 5696 : Windows UI Validation | Fixed | 4 - Live with | 3 - Low | AdamMC | 6 | 2019-09-28 | Decision machine is down | SPRINT | Design | SIT2 | WEB1 | Field b is missing on Windows UI
30 | ABCD 5696 : Field is missing on Windows UI | JonasK | 2017-07-30 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 2 | 2017-08-01 | Decision machine is down | SPRINT | Development Documentation | Sprint5 | WEB1 | Field c is missing on Windows UI
31 | ABCD 5696 : Field value is different on Windows UI | HannahK | 2017-09-13 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 4 | 2017-09-17 | Decision machine is down | SPRINT | Development Documentation | Sprint1 | WEB1 | Field b is showing different value
32 | ABCD 5696 : Field value is different on Windows UI | HannahK | 2018-02-04 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | EgonT | 15 | 2018-02-19 | Decision machine is down | SPRINT | Development Documentation | Sprint5 | WEB1 | Field c is showing different value
33 | ABCD 2258 : Windows Application is showing low performance on heavy load | ClaudiaT | 2019-07-19 | ABCD 1147 : Windows PAT Validation | Fixed | 3 - Non-Critical | 2 - Medium | EgonT | 11 | 2019-07-30 | Decision machine is down | SPRINT | Development Documentation | SIT1 | WEB1 | The performance of the system is lagging by 30 seconds on heavy load.
34 | ABCD 2258 : Web Application is showing low performance on heavy load | ClaudiaT | 2019-07-18 | ABCD 2258 : Web PAT Validation | Deferred | 4 - Live with | 3 - Low | HelgeD | 1 | 2019-07-19 | Decision machine is down | SPRINT | Development Documentation | SIT1 | WEB1 | The performance of the system is lagging by 30 seconds on heavy load.
35 | ABCD 2258 : Web Application is showing low performance on heavy load | ClaudiaT | 2017-03-22 | ABCD 2258 : Web PAT Validation | Production | 1 - Showstopper | 1 - High | HelgeD | 5 | 2017-03-27 | We are looking for the root cause | UAT | Design | SIT1 | WEB1 | The performance of the system is lagging by 30 seconds on heavy load.
36 | ABCD 5696 : Status coming is different on Windows UI | JonasK | 2017-11-08 | ABCD 5696 : Windows UI Validation | Closed | 4 - Live with | 3 - Low | AleksanderT | 1 | 2017-11-09 | MQ is down | UAT | Code | SIT1 | WEB1 | Status shown is declined instead of approved
37 | ABCD 5696 : Status coming is different on Windows UI | JonasK | 2017-11-29 | ABCD 5696 : Windows UI Validation | Closed | 4 - Live with | 3 - Low | NoahMC | 15 | 2017-12-14 | MQ is down | UAT | Code | SIT1 | WEB1 | Status shown is Passed instead of failed
38 | ABCD 5696 : Status coming is different on Windows UI | JonasK | 2018-08-13 | ABCD 5696 : Windows UI Validation | Closed | 1 - Showstopper | 1 - High | NoahMC | 3 | 2018-08-16 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SPRINT | Code | CR1 | WEB1 | Status shown is Passed instead of failed
39 | ABCD 5696 : Status coming is different on Windows UI | JonasK | 2018-08-25 | ABCD 5696 : Windows UI Validation | Deferred | 4 - Live with | 3 - Low | NoahMC | 14 | 2018-09-08 | Decision machine is down | SPRINT | Code | SIT2 | WEB3 | Status shown is declined instead of approved
40 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2016-11-30 | ABCD 1147 : Windows PAT Validation | Deferred | 2 - Critical | 1 - High | AleksanderT | 4 | 2016-12-04 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | PROD | Code | SIT2 | Windows1 | The performance of the system is lagging by 30 seconds on heavy load.
41 | ABCD 2258 : Web Application is showing low performance on normal load | JonasK | 2019-11-12 | ABCD 2258 : Web PAT Validation | Production | 2 - Critical | 1 - High | HelgeD | 13 | 2019-11-25 | We are looking for the root cause | SIT | Code | SIT2 | Windows1 | The performance of the system is lagging by 30 seconds on normal load.
42 | ABCD 2258 : Web Application is showing low performance on normal load | HannahK | 2017-02-24 | ABCD 2258 : Web PAT Validation | Rejected | 2 - Critical | 1 - High | EgonT | 2 | 2017-02-26 | We are looking for the root cause | SIT | not yet analyzed | CR1 | Windows1 | The performance of the system is lagging by 30 seconds on normal load.
43 | ABCD 5696 : Field is missing on Windows UI | ClaudiaT | 2016-09-17 | ABCD 5696 : Windows UI Validation | Fixed | 2 - Critical | 1 - High | AdamMC | 14 | 2016-10-01 | CB Pull is down | SIT | not yet analyzed | Sprint5 | Windows1 | Field d is missing on Windows UI
44 | ABCD 5696 : Field is missing on Windows UI | ClaudiaT | 2018-10-18 | ABCD 5696 : Windows UI Validation | Fixed | 4 - Live with | 3 - Low | AdamMC | 4 | 2018-10-22 | CB Pull is down | SIT | Design | SIT2 | Windows1 | Field e is missing on Windows UI
45 | ABCD 5696 : Field is missing on Windows UI | ClaudiaT | 2020-11-17 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 15 | 2020-12-02 | Decision machine is down | SIT | Design | SIT2 | Windows1 | Field f is missing on Windows UI
46 | ABCD 2258 : Windows Application is showing low performance on normal load | UlrichN | 2020-07-24 | ABCD 1147 : Windows PAT Validation | Fixed | 4 - Live with | 3 - Low | AleksanderT | 4 | 2020-07-28 | Decision machine is down | SIT | Development Documentation | SIT2 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
47 | ABCD 2258 : Windows Application is showing low performance on normal load | UlrichN | 2016-10-24 | ABCD 1147 : Windows PAT Validation | Closed | 3 - Non-Critical | 2 - Medium | EgonT | 14 | 2016-11-07 | Decision machine is down | UAT | Development Documentation | CR1 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
48 | ABCD 1231: Field is added on Web UI | ClaudiaT | 2019-09-23 | ABCD 1231 : Web UI Validation | Closed | 3 - Non-Critical | 2 - Medium | EgonT | 11 | 2019-10-04 | Decision machine is down | SPRINT | Development Documentation | PAT Apr | WEB2 | Field c is added on web UI
49 | ABCD 1231: Field is added on Web UI | PeterD | 2019-01-18 | ABCD 1231 : Web UI Validation | Closed | 4 - Live with | 3 - Low | HelgeD | 14 | 2019-02-01 | Decision machine is down | UAT | Development Documentation | Sprint1 | WEB2 | Field d is added on web UI
50 | ABCD 1231: Field is added on Web UI | JonasK | 2017-11-30 | ABCD 1231 : Web UI Validation | Deferred | 4 - Live with | 3 - Low | ElisabethD | 15 | 2017-12-15 | We are looking for the root cause | SIT | not yet analyzed | Sprint1 | WEB3 | Field f is added on web UI
51 | ABCD 1231: Status coming on Web UI is different | JonasK | 2020-04-14 | ABCD 1231 : Web UI Validation | Deferred | 4 - Live with | 3 - Low | AleksanderT | 12 | 2020-04-26 | We are looking for the root cause | SIT | not yet analyzed | CR1 | Windows5 | Status shown is Passed instead of failed
52 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2019-07-31 | ABCD 1147 : Windows PAT Validation | Fixed | 2 - Critical | 1 - High | NoahMC | 5 | 2019-08-05 | We are looking for the root cause | SIT | Code | SIT1 | Windows2 | The performance of the system is lagging by 30 seconds on heavy load.
53 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2016-07-21 | ABCD 1147 : Windows PAT Validation | Fixed | 2 - Critical | 1 - High | NoahMC | 9 | 2016-07-30 | We are looking for the root cause | SIT | Code | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on heavy load.
54 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2016-01-02 | ABCD 1147 : Windows PAT Validation | Production | 2 - Critical | 1 - High | NoahMC | 11 | 2016-01-13 | MQ is down | SIT | Code | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on heavy load.
55 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2020-10-04 | ABCD 1147 : Windows PAT Validation | Closed | 2 - Critical | 1 - High | NoahMC | 11 | 2020-10-15 | MQ is down | SIT | Code | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on heavy load.
56 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2019-09-01 | ABCD 1147 : Windows PAT Validation | Closed | 2 - Critical | 1 - High | ElisabethD | 3 | 2019-09-04 | CB Pull is down | SIT | Code | SIT1 | Windows1 | The performance of the system is lagging by 30 seconds on heavy load.
57 | ABCD 5696 : Field is added on Windows UI | HannahK | 2017-07-10 | ABCD 5696 : Windows UI Validation | Rejected | 3 - Non-Critical | 2 - Medium | InesK | 6 | 2017-07-16 | CB Pull is down | SIT | Code | SIT1 | Windows1 | Field b is added on UI
58 | ABCD 5696 : Field is added on Windows UI | UlrichN | 2018-10-22 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 3 | 2018-10-25 | CB Pull is down | UAT | Code | Sprint5 | Windows1 | Field c is added on UI
59 | ABCD 5696 : Field is added on Windows UI | UlrichN | 2017-01-07 | ABCD 5696 : Windows UI Validation | Fixed | 3 - Non-Critical | 2 - Medium | AdamMC | 7 | 2017-01-14 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | UAT | Code | Sprint1 | Windows5 | Field d is added on UI
60 | ABCD 2258 : Windows Application is showing low performance on normal load | PeterD | 2017-12-18 | ABCD 1147 : Windows PAT Validation | Closed | 3 - Non-Critical | 2 - Medium | ElisabethD | 5 | 2017-12-23 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | PROD | Code | Sprint1 | Windows2 | The performance of the system is lagging by 30 seconds on normal load.
61 | ABCD 2258 : Windows Application is showing low performance on normal load | ClaudiaT | 2020-08-25 | ABCD 1147 : Windows PAT Validation | Closed | 4 - Live with | 3 - Low | AleksanderT | 10 | 2020-09-04 | Decision machine is down | SPRINT | Code | CR1 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
62 | ABCD 2258 : Windows Application is showing low performance on normal load | ClaudiaT | 2020-05-08 | ABCD 1147 : Windows PAT Validation | Closed | 4 - Live with | 3 - Low | ElisabethD | 14 | 2020-05-22 | Decision machine is down | UAT | Code | SIT2 | WEB2 | The performance of the system is lagging by 30 seconds on normal load.
63 | ABCD 2258 : Web Application is showing low performance on heavy load | ClaudiaT | 2020-10-10 | ABCD 2258 : Web PAT Validation | Fixed | 4 - Live with | 3 - Low | InesK | 14 | 2020-10-24 | Decision machine is down | UAT | Code | SIT2 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
64 | ABCD 2258 : Web Application is showing low performance on heavy load | KatharinaN | 2020-10-18 | ABCD 2258 : Web PAT Validation | Fixed | 4 - Live with | 3 - Low | HelgeD | 15 | 2020-11-02 | Decision machine is down | PROD | Design | SIT2 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
65 | ABCD 2258 : Web Application is showing low performance on heavy load | PeterD | 2017-10-07 | ABCD 2258 : Web PAT Validation | Fixed | 4 - Live with | 3 - Low | EgonT | 5 | 2017-10-12 | We are looking for the root cause | PROD | Design | PAT Apr | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
66 | ABCD 2258 : Web Application is showing low performance on normal load | PeterD | 2019-09-08 | ABCD 2258 : Web PAT Validation | Production | 2 - Critical | 1 - High | EgonT | 8 | 2019-09-16 | We are looking for the root cause | SIT | Development Documentation | CR1 | WEB3 | The performance of the system is lagging by 30 seconds on normal load.
67 | ABCD 2258 : Web Application is showing low performance on normal load | HannahK | 2020-07-12 | ABCD 2258 : Web PAT Validation | Rejected | 2 - Critical | 1 - High | NoahMC | 2 | 2020-07-14 | MQ is down | SIT | Development Documentation | UAT1 | Windows5 | The performance of the system is lagging by 30 seconds on normal load.
68 | ABCD 2258 : Windows Application is showing low performance on heavy load | PeterD | 2017-11-30 | ABCD 1147 : Windows PAT Validation | Production | 2 - Critical | 1 - High | NoahMC | 11 | 2017-12-11 | MQ is down | SIT | Development Documentation | Sprint1 | Windows5 | The performance of the system is lagging by 30 seconds on heavy load.
69 | ABCD 2258 : Windows Application is showing low performance on heavy load | PeterD | 2016-10-05 | ABCD 1147 : Windows PAT Validation | Closed | 2 - Critical | 1 - High | NoahMC | 9 | 2016-10-14 | Decision machine is down | SIT | Development Documentation | Sprint1 | WEB3 | The performance of the system is lagging by 30 seconds on heavy load.
70 | ABCD 5696 : Field value is different on Windows UI | JonasK | 2018-04-20 | ABCD 5696 : Windows UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 5 | 2018-04-25 | Decision machine is down | SIT | Development Documentation | Sprint1 | Windows4 | Field d is showing different value
71 | ABCD 5696 : Field value is different on Windows UI | JonasK | 2020-10-30 | ABCD 5696 : Windows UI Validation | Closed | 2 - Critical | 1 - High | NoahMC | 15 | 2020-11-14 | Decision machine is down | SIT | Development Documentation | SIT1 | Windows4 | Field e is showing different value
72 | ABCD 2258 : Windows Application is showing low performance on normal load | KatharinaN | 2020-01-08 | ABCD 1147 : Windows PAT Validation | Rejected | 2 - Critical | 1 - High | NoahMC | 15 | 2020-01-23 | We are looking for the root cause | SIT | Development Documentation | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on normal load.
73 | ABCD 2258 : Windows Application is showing low performance on normal load | ElisabethD | 2017-08-06 | ABCD 1147 : Windows PAT Validation | Production | 1 - Showstopper | 1 - High | NoahMC | 4 | 2017-08-10 | We are looking for the root cause | PAT | Development Documentation | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on normal load.
74 | ABCD 2258 : Windows Application is showing low performance on normal load | ClaudiaT | 2016-02-05 | ABCD 1147 : Windows PAT Validation | New | 1 - Showstopper | 1 - High | NoahMC | 7 | 2016-02-12 | We are looking for the root cause | UAT | Development Documentation | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on normal load.
75 | ABCD 1231: Status coming on Web UI is different | ClaudiaT | 2018-01-05 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | AleksanderT | 11 | 2018-01-16 | CB Pull is down | PROD | Development Documentation | SIT1 | Windows4 | Status shown is declined instead of approved
76 | ABCD 1231: Status coming on Web UI is different | ClaudiaT | 2019-03-16 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | ElisabethD | 3 | 2019-03-19 | CB Pull is down | SIT | Development Documentation | UAT1 | Windows1 | Status shown is declined instead of approved
77 | ABCD 1231: Status coming on Web UI is different | ClaudiaT | 2020-09-18 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | AdamMC | 12 | 2020-09-30 | CB Pull is down | SIT | not yet analyzed | UAT1 | Windows1 | Status shown is Passed instead of failed
78 | ABCD 1231: Status coming on Web UI is different | KatharinaN | 2020-11-23 | ABCD 1231 : Web UI Validation | New | 4 - Live with | 3 - Low | AleksanderT | 3 | 2020-11-26 | We are looking for the root cause | SIT | not yet analyzed | Sprint1 | Windows1 | Status shown is declined instead of approved
79 | ABCD 1231: Field is added on Web UI | JonasK | 2016-04-12 | ABCD 1231 : Web UI Validation | New | 4 - Live with | 3 - Low | ElisabethD | 5 | 2016-04-17 | We are looking for the root cause | SIT | Code | Sprint1 | Windows5 | Field e is added on web UI
80 | ABCD 1231: Field is added on Web UI | JonasK | 2017-12-02 | ABCD 1231 : Web UI Validation | Fixed | 4 - Live with | 3 - Low | InesK | 13 | 2017-12-15 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | Code | Sprint1 | Windows2 | Field g is added on web UI
81 | ABCD 1231: Field is missing on Web UI | JonasK | 2019-02-24 | ABCD 1231 : Web UI Validation | Fixed | 4 - Live with | 3 - Low | HelgeD | 8 | 2019-03-04 | Decision machine is down | SIT | Code | Sprint1 | WEB2 | Field d is missing on Web UI
82 | ABCD 1231: Field is missing on Web UI | JonasK | 2018-06-17 | ABCD 1231 : Web UI Validation | New | 4 - Live with | 3 - Low | AdamMC | 11 | 2018-06-28 | Decision machine is down | SIT | Code | PAT Apr | WEB2 | Field e is missing on Web UI
83 | ABCD 1231: Field is missing on Web UI | JonasK | 2017-01-14 | ABCD 1231 : Web UI Validation | New | 3 - Non-Critical | 2 - Medium | ElisabethD | 6 | 2017-01-20 | Decision machine is down | PROD | Code | SIT2 | WEB2 | Field f is missing on Web UI
84 | ABCD 2258 : Windows Application is showing low performance on heavy load | JonasK | 2018-04-04 | ABCD 1147 : Windows PAT Validation | Production | 3 - Non-Critical | 2 - Medium | NoahMC | 7 | 2018-04-11 | Decision machine is down | SPRINT | Code | SIT2 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
85 | ABCD 2258 : Windows Application is showing low performance on heavy load | KatharinaN | 2020-05-31 | ABCD 1147 : Windows PAT Validation | Rejected | 3 - Non-Critical | 2 - Medium | NoahMC | 7 | 2020-06-07 | Decision machine is down | UAT | not yet analyzed | UAT1 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
86 | ABCD 2258 : Windows Application is showing low performance on heavy load | ElisabethD | 2020-07-20 | ABCD 1147 : Windows PAT Validation | New | 3 - Non-Critical | 2 - Medium | AleksanderT | 6 | 2020-07-26 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | UAT | not yet analyzed | SIT1 | WEB2 | The performance of the system is lagging by 30 seconds on heavy load.
87 | ABCD 5696 : Field is added on Windows UI | UlrichN | 2017-01-30 | ABCD 5696 : Windows UI Validation | New | 2 - Critical | 1 - High | ElisabethD | 12 | 2017-02-11 | We are looking for the root cause | SPRINT | Business Requirements | SIT1 | Windows5 | Field e is added on UI
88 | ABCD 5696 : Field is added on Windows UI | UlrichN | 2016-05-27 | ABCD 5696 : Windows UI Validation | New | 4 - Live with | 3 - Low | InesK | 11 | 2016-06-07 | MQ is down | SPRINT | Design | SIT1 | Windows5 | Field f is added on UI
89 | ABCD 2258 : Windows Application is showing low performance on heavy load | HannahK | 2016-07-11 | ABCD 1147 : Windows PAT Validation | New | 4 - Live with | 3 - Low | EgonT | 4 | 2016-07-15 | MQ is down | PAT | Design | SIT1 | WEB3 | The performance of the system is lagging by 30 seconds on heavy load.
90 | ABCD 2258 : Windows Application is showing low performance on heavy load | KatharinaN | 2018-05-02 | ABCD 1147 : Windows PAT Validation | Production | 4 - Live with | 3 - Low | EgonT | 13 | 2018-05-15 | CB Pull is down | PROD | Development Documentation | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on heavy load.
91 | ABCD 2258 : Windows Application is showing low performance on heavy load | ElisabethD | 2016-03-21 | ABCD 1147 : Windows PAT Validation | Rejected | 2 - Critical | 1 - High | ElisabethD | 13 | 2016-04-03 | CB Pull is down | PAT | Development Documentation | SIT1 | Windows4 | The performance of the system is lagging by 30 seconds on heavy load.
92 | ABCD 1231: Field value is different on Web UI | ClaudiaT | 2020-03-27 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | HelgeD | 2 | 2020-03-29 | We are looking for the root cause | PROD | Development Documentation | SIT1 | Windows4 | Field A is showing different value
93 | ABCD 1231: Field value is different on Web UI | ClaudiaT | 2016-08-10 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | AleksanderT | 3 | 2016-08-13 | Decision machine is down | PROD | Development Documentation | SIT1 | Windows4 | Field A is showing different value
94 | ABCD 1231: Field value is different on Web UI | ClaudiaT | 2019-11-09 | ABCD 1231 : Web UI Validation | New | 2 - Critical | 1 - High | ElisabethD | 13 | 2019-11-22 | Decision machine is down | UAT | Business Requirements | UAT1 | Windows4 | Field A is showing different value
95 | ABCD 2258 : Windows Application is showing low performance on normal load | ClaudiaT | 2020-08-08 | ABCD 1147 : Windows PAT Validation | Fixed | 2 - Critical | 1 - High | InesK | 14 | 2020-08-22 | Decision machine is down | UAT | Business Requirements | Sprint1 | Windows4 | The performance of the system is lagging by 30 seconds on normal load.
96 | ABCD 1231: Field value is different on Web UI | ClaudiaT | 2016-11-28 | ABCD 1231 : Web UI Validation | Production | 4 - Live with | 3 - Low | HelgeD | 13 | 2016-12-11 | Decision machine is down | UAT | Code | PAT Apr | Windows2 | Field A is showing different value
97 | ABCD 1231: Field is added on Web UI | PeterD | 2019-03-06 | ABCD 1231 : Web UI Validation | Rejected | 4 - Live with | 3 - Low | AdamMC | 14 | 2019-03-20 | We are looking for the root cause | PAT | Code | SIT2 | WEB3 | Field j is added on web UI
98 | ABCD 1231: Field is added on Web UI | JonasK | 2020-05-15 | ABCD 1231 : Web UI Validation | New | 4 - Live with | 3 - Low | AdamMC | 2 | 2020-05-17 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | Code | SIT2 | WEB2 | Field i is added on web UI
99 | ABCD 1231: Field value is different on Web UI | JonasK | 2016-12-12 | ABCD 1231 : Web UI Validation | New | 1 - Showstopper | 1 - High | NoahMC | 5 | 2016-12-17 | Time is an endless loop. So we need time to fix this. But there is a loop hole. | SIT | Code | UAT1 | WEB2 | Field A is showing different value
100 | ABCD 1231: Field is missing on Web UI | JonasK | 2019-09-07 | ABCD 1231 : Web UI Validation | New | 1 - Showstopper | 1 - High | NoahMC | 7 | 2019-09-14 | Decision machine is down | SPRINT | Code | SIT1 | WEB2 | Field g is missing on Web UI